## Sheet1
Date / Day | Standard Task | Other activities | Other activity time | Task | Completion Time(In minutes)
09/03/2026 (Monday) | Tested API |  |  | Tested APIs in account service to get to know that the All the informations are getting rightly storing and fetching properly | 45
| Created Solution API |  |  | Crafted the solution API to Fetch the Solution through User id, Solution name. | 240
| Creation API |  |  | Crafted the solution API to Fetch the Solution through Scope. | 240
10/03/2026 (Tuesday) | Understanding |  |  | Understand how can i implement specification in it and how to decrease its response time | 30
| Creation of API |  |  | Created an API to fetch the Project from given range date in which, I used SQL query which later on i understand that it will increase the response time of the API | 240
| Optimization Of API |  |  | Optimized the API using the concepts, I learn yesterday. I implemented specification in Range Date so that , a one can easily fetch through any entity. | 240
| Modification in API |  |  | Tested all the endpoints , I make and make sure that the responses are accurate. | 30
2026-03-11 | On Leave
12/03/2026 (Thursday) | Created API |  |  | Created Product API where already submitted product is get updated through product id | 240
| Created API |  |  | Tested the newly created Update product API, tested all the edge cases there and move forward to project API | 30
| Created of API |  |  | Created Get API to fetch the project by project Status Tested that API . with this Also created API to Fetch Project through milestone and tested it as well. | 240
13/03/2026 (Friday) | Testing API |  |  | Tested all the API build by me previously and note down there response timing and understand how can i optimize them | 240
| Modification in API |  |  | Slight modifications in API which was build by me previously under the suggestions of senior developer | 100
| Database Test |  |  | Making sure that the APIs running are accurtely storing data and fetching it properly without giving any error. | 100
| Commit Code |  |  | Commit all the code that were written previously by me after the review of senior developers | 90
16/03/2026 (Monday) | Tested ERP |  |  | Tested the newly build CRM. Testing the sales service are properly generating leads , estimates are properly build or not. reported some navigation issue to senior developer | 180
| Tested ERP |  |  | Tested the Account Service. Checked there that company apporovals are properly changing there status and unbilled are accurately creating or not reported bug of update status in unbilled giving error. | 180
| Tested ERP |  |  | Tested the Operation Service, making sure that project is making without throwing any error, reported timeline issue to senior developers | 180
17/03/2026 (Tuesday) | Tested Account Service |  |  | Tested all the APIs of account service making sure all the endpoints are properly working | 180
| Tested ERP |  |  | Tested ERP , navigation not working properly reported a bug to senior developer. | 180
| Understanding Error |  |  | Understanding the error that poping while testing the erp through inspect section and reported all the APIs that was throwing error | 150
18/03/2026 (Wednesday) | Tested Database |  |  | Tested and reassure that the data is storing and fetching from the Database properly | 120
| Tested ERP |  |  | Tested ERP making sure that the company must be approved before unbilled, and invoice is properly generating | 210
| Tested ERP |  |  | Reported a bug in invoice as it does not calculate the remaining due properly, reported the error response is not understandable to the user easily. Making sure that the estimate pdf have all the required entries | 210
19/03/2026 (Thursday) | TESTED ERP |  |  | Tested all the ERP making sure each and every thing is working properly and does not have any bug in it. | 330
| Meeting |  |  |  | 130
| Check |  |  | Check and write all the requirement that reported by the other teams to make ensure that the ERP would be smooth for the users. Consider there response and make sure that the all the requirements should implement properly | 80
2026-03-20 | Created API |  |  | Created API to fetch all the estimates of that particular estimate id | 180
| Created API |  |  | Created API to fetch all the estimates thorugh company id | 240
| Tested API |  |  | Tested the API making sure that it shares an accurate response . Commit the API. | 150
21/03/2026 (Saturday) | Tested ERP |  |  | Tested the ERP all day, the reported bugs are fixed or not, some features that are asked by other teams are implemented properly and sending a proper response or not. Reporting some minor bugs about invoice in accounts and in the project section in operation | 340
| Activity |  |  |  | 80
| ERP Modification |  |  | Write all the modifcations and Add Ons that have to be made in ERP | 120
23/03/2026 (Monday) | Created API |  |  | Created API of project timeline where all the project should fetch by user id, created dtos, service logic and controller. Used Pagination in it to fetch the limited response which enhances the API response as well | 240
| Created Feign Client |  |  | Created Feign client in lead and connect it to operation so that all the project activity timeline canbe fetched from the account | 240
| Tested Created API |  |  | Tested created api there endpoints and make sure that it is returning proper response. | 30
24/03/2026 (Tuesday) | Created API |  |  | Created Project Summary API where it will fetch all the status, assigned user, comment, notes,and everything that is required. used Get HTTP method in project activity controller , create a logic in service and fetch the details from repo, map the Milestone Summary , comment and notes | 300
| Modification |  |  | After testing get some errors and incomplete response. Modified all the layers properly so that it can provide accurate output | 180
| Understanding the requirement |  |  | Understanding the requirement of the senior developer about the new filter option in project section | 50
25/03/2026 (Wednesday) | Created API |  |  | Created the required API with filter, Aplied dynamic filtering using specification in it , can be easily fetch through status, assignee, range date | 180
| Tested ERP |  |  | Tested Updated ERP | 240
| Report Errors |  |  | Report the Errors to senior developers and give some add on ideas | 90
26/03/2026 (Thursday) | Tested Lead |  |  | Tested and Verified Lead data in the Database and reported mismatch entities in the database | 360
| Created API |  |  | Created Project API to fetch project by user id | 120
27/03/2026 (Friday) | Tested ERP |  |  | Tested Updated ERP | 300
| Tested ERP |  |  | Test Reported Errors are updated or not | 240
30/03/2026 (Monday) | Created API |  |  | Developed API to Fetch Project Summary, all the notes and comments will also get fetch through this | 240
| Tested API |  |  | Tested all the edge cases of created API | 120
| Tested ERP |  |  | Tested the Updated ERP and reported bugs | 120
31/03/2026 (Tuesday) | Tested Account Service |  |  | Tested Account Service and making sure that the all the values are calculating properly | 240
| Tested Operation |  |  | Tested Operation service making sure that the project are making properly or not | 240
| Tested ERP |  |  | Tested By Making new leads | 30
01/04/2026 (Wednesday) | Reported |  |  | Reported the bugs while testing the erp | 240
| Understand |  |  | Understanding the requirements and the flow of Lead | 240
| Tested ERP |  |  | Test the API endpoints through postman | 30
02/04/2026 (Thursday) | Reported |  |  | Reported the Account error , calculations in unbilled and invoices | 240
| Tested Lead |  |  | Tested Lead by making multiple units in and making sure that we can work with it or not | 240
| Report |  |  | Reported the Lead units Errors | 30
03/04/2026 (Friday) | Tested & Reported |  |  | Tested and Reported the multiple errors while making lead and multiple units. | 240
270
| Created API |  |  | Modified the existing API as Approval Status of Estimate by name is getting null in Database
04/04/2026 (Saturday) | Tested ERP |  |  | Tested Updated ERP | 480
06/04/2026 (Monday) | Modified API |  |  | Modified API Project, where projet approvedbyname getting null. | 240
| Tested ERP |  |  | Tested the Updated ERP from the starting | 120
| Reported |  |  | Report the Errors to the Senior Dev | 120